S91: Board Resolution

Song Da 9.01 JSC announces the Board Resolution approved on 24/07/2012 as follows:

- Operating result of first 6 months of 2012

| No | Description | Unit | Plan of QII/2012 | Result of QII/2012 | % complete of plan | Result of first 6 months of 2012 | % complete of first 6 months of 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Productivity | VND 1,000 | 38,522,366 | 31,166,812 | 81% | 62,082,565 | 54% |
| 2 | Sales |  | 65,230,583 | 36,001,246 | 55% | 44,256,107 | 35% |
| 3 | Revenue |  | 59,300,530 | 34,576,213 | 58% | 41,707,441 | 36% |
| 4 | Payable for State |  | 4,787,330 | 968,482 | 20% | 1,403,008 | 18% |
| 5 | Profit before tax |  | 3,786,873 | 1,359,007 | 36% | 2,394,651 | 23% |
| 6 | Average income (VND million/month/person) |  | 6,658 | 5,818 | 87% | 6,207 | 108% |

- Projects progress

| No | Project | Progress |  |  |
| --- | --- | --- | --- | --- |
|  |  | Beginning | On progress | Completed |
| 1 | Xekaman 1 |  | Digging factory base period 1 | Exploded CNN base period 2 |
| 2 | Dong Nai 5 |  | Overfall dam; Digging Righ shoulder base | Digging and leveling no 2 road |

- Investment: VND billion 0/ 7.5, due to lack of capital

- Assess results

- Liquidated projects: No 51 national road, Huong Son and Sesan 4;

- Signed contract reference Dong Nai 5 Hydroelectricity for No 5 package with the value of VND billion 177.4;

- Discuss with Song Da Corporation on estimation of Dong Nai 5 Hydroelectricity;

- Attened biding package No 19-AK for terminal construction of A Roang Hydroelectricity – Thua Thien Hue province;

- Maitained and repaired: VND billion 0.32/ 1.382 (23% of QII plan); cumulatived VND billion 0.8 (28% of 2012 plan).

- Plan of last 6 months of 2012

| No | Description | Unit | Plan of QIII/2012 | Plan of last 6 months of 2012 | Note |
| --- | --- | --- | --- | --- | --- |
| 1 | Productivity | VND 1,000 | 20,410,921 | 57,685,302 |  |
| 2 | Sales |  | 45,287,644 | 81,564,920 |  |
| 3 | Revenue |  | 41,170,585 | 72,675,311 |  |
| 4 | Payable for State |  | 5,010,607 | 6,461,307 |  |
| 5 | Profit before tax |  | 5,472,023 | 8,094,248 |  |
| 6 | Average income (VND million/month/person) |  | 5,570 | 5,719 |  |

- Xekaman 1

- Completed digging Factory base: period 1: 30/07/2012, up to CD140, 60,000m3; period 2: 31/08/2012, 120,000m3 and 09/2012, transferring hole bases up to CD112;

- Leveling and exploring No 3 stone mine: 31/12/2012, 320,000m3;

- Emtank low-stream dam.

- Dong Nai 5 Hydroelectricity

- Tune 2 working road (Km3 – Km10): 30/09/2012;

- Overfall dam Km5+117: 30/11/2012;

- Leveling stone mine Period 2;

- Demolished vertical dam: 30/10/2012;

- Digged base of Right shoulder: QIII/2012: 320,000m3 and Last 6 months of 2012: 960,000m3;

- Prepared river intercepting: QIV/2012.