AAA: General Mandate 2016

On 17 Oct 2016, An Phat Plastic and Green Environment Joint Stock Company announced the General Mandate 2016 as follows:

Article 1: Approve the plan for investment and building Factory No.8 as follows:

- Name of project: Multi-film packaging production factory

- Location: Nam Sach Town, Nam Sach District, Hai Duong Province

- Area: 98.088 m2

- Capacity: 7,200 tons/ year

- Operation time: 50 years since the area is assigned to the Company

- Operation purpose: Produce multi-film packaging

- Total investment: VND 500,646,482,000

- Expected progress:

+ Time of finishing procedure for construction, investment: before Dec 2016

+ Construction time: from Jan 2017 to Dec 2017

+ Time of installing machinery, equipment: from Oct 2017 to Dec 2017

+ Labor recruitment: from Sep to Dec 2017

+ Commission: Jan 2018

+ Officially come into operation: from Apr 2018

Voting rate: 83.78%

Article 2: Authorize Board of Directors to choose implementation time, mobilize capital, carry out construction, and install machines and other work to build Factory No. 8

Voting rate: 83.78%

Article 3: Enforcement

Members of Board of Directors, General Director and shareholders take responsibility for performing this General Mandate.