# NCS: Report on use of proceeds

On 20/10/2017, Noibai Catering Services Joint Stock Company announced report on the use of proceeds as follows:

- Public stock offering:

- Name of share: Share of Noibai Catering Services Joint Stock Company

- Type of share: Common share

- Par value: VND 10,000

- Number of shares offered: 3,999,543 shares

- Total collection:

Total collection from the public offering: VND 39,803,590,000

Total expenses: VND 20,060,000

## Net collection from the offering VND 39,782,912,339

- Start date: 20/10/2016

- Finish date: 26/12/2016

### USE OF PROCEEDS

- Progress of the project published according to the Prospectus

+ In 09/2016: basically complete the land clearance, rent pond lands of People’s Committee of Phu Minh Commune and break the land on September or October of 2016;

+ Implement the bidding package in September to start constructing in the late of November of 2016;

+ In the beginning of 2017: Select equipment bidding packages;

+ Quarter I/2018: Receipt and hand over the structure;

+ Quarter II/2018: Start using and exploiting the structure;

+ 2024-2025: Implement the 2nd step

- Current progress of the project:

+ Completed the land clearance, rented pond lands of People’s Committee of Phu Minh Commune and broke the land on September or October of 2016;

Started constructing on 24/11/2016

| No | Use of proceeds | Collection from the public offering (VND) | Amount used until 20/10/2017 (VND) |
| --- | --- | --- | --- |
| 1 | Liquidation of the 1st stage of the construction bidding package | 39,782,912,339 | 39,782,912,339 |
|  | Total | 39,782,912,339 | 39,782,912,339 |

- Changes, adjustments (if any) and reasons: None