BBS: Report on the progress of using the proceeds from public stock offering

On 27/04/2017, Vicem Packaging But Son JSC announced the report on the progress of using the proceeds from public stock offering as follows:

1. The progress announced in the prospectus

| No. | Item | Value (VND billion) | Capital source (VND billion) |  |  | Expected time of disbursement |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paid-in capital | Capital from offering | Loans |  |
| 1 | Transfer the whole asset attached to land use right | 7.4 | 7.4 | 0 | 0 | Quarter 1 – quarter 2.2016 |
| 2 | Build warehouse and auxiliary works | 22.6 | 0.4 | 21.2 | 1 | Quarter 3 – quarter 4.2016 |
| 3 | Equipment and machinery | 60.0 | 16 | 0 | 44 | Quarter 3.2016 – quarter 2.2017 |

2. The current progress

| No. | Item | Disbursed amount | Status |
| --- | --- | --- | --- |
| 1 | Transfer the whole asset attached to land use right | 8,015,000,000 | Completed |
| 2 | Build warehouse and auxiliary works | 20,587,734,100 | 91.1% of completion |
| 3 | Equipment and machinery | 11,993,906,826 | 20% of completion |

Proceeds from stock offering: VND 21,202,300,000

Total cost for the offering: VND 229,956,000

Total net proceeds from the offering: VND 20,972,344,000