## HFC: Notice on the use of proceeds from the public offering

On 14/03/2018, Hanoi Petrol Fuel Joint Stock Company noticed the use of proceeds from the public offering as follows:

# Share

- Name of share: share of Hanoi Petrol Fuel Joint Stock Company

- Type of share: common share

- Par value: VND 10,000/ share

- Number of shares offered: 3,989,999 shares. In which:

+ Public offering for existing shareholders: 2,100,000 shares

+ Issue additionally shares to increase the capital from owners’ equity: 1,112,999 shares

+ Issue additionally shares to implement the dividend payment: 672,000 shares

+ Issue additionally shares under ESOP: 105,000 shares

- Total amount of proceeds: VND 22,050,000,000

- Starting date: 24/01/2017

- Finishing date: 10/03/2017

# Plan on use of proceeds from the public offering

- Progress of project disclosed in the Prospectus

| No. | Purpose | Expected amount | Expected time |
| --- | --- | --- | --- |
| 1 | Investment plan on Tam Hiep petrol station (4,100m2) | 7,094,000,000 | Q.IV/2016– Q.I/2017 |
| 2 | Investment plan on petrol station at Dan Phuong District (3,300m2) | 14,956,000,000 | Q/IV/2016– Q.I/2017 |
|  | Total | 22,050,000,000 |  |

- Current progress of project:

| No. | Purpose | Disbursed amount | Completion time |
| --- | --- | --- | --- |
| 1 | Investment plan on Tam Hiep petrol station (4,100m2) | 7,094,000,000 | Q.I/2017 |
| 2 | Investment plan on petrol station at Dan Phuong District (3,300m2) | 0 | Q/IV/2018 |
|  | Total | 7,094,000,000 |  |

- Changes, adjustments: Following the Resolution No. 05/2018/NQ/HFC-HDQT issued on 13/03/2018, the investment project on petrol station at Dan Phuong District (3,300m2), the company has implemented following the requirements of households, the time of clearance was longer then expectation and real area was larger. In 01/2018, the Company completed the procedures on clearance and receiving land transfer; however, the plan changed, so the progress of project was longer. Board of Directors has adjusted the use of proceeds into Q.IV/2018.